## 21 Backlog
Final Implementation Backlog
SIMULATED DATA - NOT ACTUAL VELOOP DATA. Status legend: Confirmed / Proposed / To Be Verified. No proposed item is claimed to exist in production.
Priority | Requirement | Reason | Dependency | Owner | Stage
Critical | Stable, immutable user_id issued at registration | Cross-event analysis (A002) | Authentication | Engineering | Prelaunch
Critical | Unique event_id with idempotent writes | Duplicate events inflate KPIs (10 duplicates in sample audit) | Event service | Engineering | Prelaunch
Critical | Wallet transaction_id and append-only ledger | Reconciliation and deduplication | Wallet | Engineering | Prelaunch
Critical | Referral table with referrer and referred IDs and stage timestamps | Referral conversion cannot be computed otherwise | Registration, Referral | Engineering | Prelaunch
Critical | Withdrawal lifecycle with requested, processing, final timestamps | Processing-time and queue KPIs | Withdrawals | Engineering | Prelaunch
Critical | Emit task_started / task_completed / task_failed events | Core earning analytics | Tasks | Engineering | Prelaunch
Critical | Emit reward_credited linked to ledger entry | Separate activity from credit | Rewards, Wallet | Engineering | Prelaunch
High | Account Status History table | Separate pre/post suspension activity | Accounts | Engineering | Prelaunch
High | Session identifier and session end rule | Funnels and session KPIs | Frontend/Backend | Engineering | Prelaunch
High | Approved enum lists (failure_category, reason_category, unit, method) | Prevents free-text drift | Product decisions | Product | Prelaunch
High | Timezone standard (UTC storage, IST reporting if needed) | Day-boundary KPIs | Event service | Engineering | Prelaunch
High | Confirm eligibility rules for pending and suspended accounts | Resolves DQ-017, DQ-026 | Policy | Product / Operations | Prelaunch
High | Raw layer + validation job + quarantine table | Quality controls | Storage | Data / Engineering | Prelaunch
High | Publish KPI definitions and DAU qualifying-event list | Reproducible metrics | Product | Analytics | Prelaunch
High | Obtain missing Task 01 simulated sheets (A003) | Complete J2/J3 testing | Program team | Admin | Immediate
Medium | Consent history capture | Compliance audit | Legal | Engineering | Prelaunch
Medium | Third-party outcome fields (provider_ref, provider_status) | Attribute external effects | Providers | Engineering | Postlaunch
Medium | Data-quality dashboard tile and alerts | Operational trust | Pipeline | Data | Postlaunch
Medium | Role-based access and hashed identifiers in analytics layer | Privacy | Governance | Data / Engineering | Prelaunch
Medium | Support ticket category tracking | Support KPIs | Operations | Operations | Postlaunch
Low | Badge/level/leaderboard analytics | Low business risk | Core events | Analytics | Postlaunch
Low | Advanced management dashboard | Needs production data | Production data | Analytics | Postlaunch